Leo Hong

Monthly Workload Report

April 2026  |  Abbvie CRO Programming Team

| 176 hrs Monthly capacity (1.0 FTE) | 144 hrs Project hours allocated |
| --- | --- |
| 0.86 Total FTE utilisation | 32 hrs Holiday / PTO |

# 1. Monthly Time Allocation

Leo's full 176-hour monthly capacity is fully committed. Project hours (144 hrs) are distributed across 6 tasks plus an unplanned buffer. No slack remains.

| Task / Project | Role | Hours | % of Project Time |
| --- | --- | --- | --- |
| REQ6076 — HEMONC_E01_DLBCL_ISS | Support (Lillian Dai) | 40 hrs | 27.8% |
| Unplanned — Abbvie buffer | Reserve | 24 hrs | 16.7% |
| REQ6621 — ONC_M19_708 | Support (Mouctar Barry) | 20 hrs | 13.9% |
| REQ6710 — ONC_M23_001 | Owner | 20 hrs | 13.9% |
| REQ6069 — ONC_M15_656 | Owner | 16 hrs | 11.1% |
| REQ6685 — ONC_M19_611 | Support (David Xu) | 16 hrs | 11.1% |
| REQ6637 — HEMONC_M21_103 | Support (Summer Yang) | 8 hrs | 5.6% |
| Holiday / PTO | — | 32 hrs | — |
| Total | — | 176 hrs | 100% |

Key observation Largest single commitment: 40 hrs supporting REQ6076 (DLBCL_ISS) — 28% of all project hours Unplanned buffer (24 hrs) is pre-assigned; if triggered, it compresses other delivery timelines Abbvie FTE = 0.68 ¦ Total FTE = 0.86 ¦ Zero buffer beyond the reserved 24 hrs

# 2. Projects Owned by Leo Hong

Leo is the named owner on 2 Abbvie requests this month, with a combined workload of 449 output items.

## REQ6069 — G_040_ONC_M15_656

| Sponsor | Abbvie |
| --- | --- |
| Study | G_040_ONC_M15_656 |
| Request | REQ6069 |
| Leo H. hours | 16 hrs |
| Rerun TFL | 385 |
| New ADaM / TFL | 0 / 0 |
| SOW | Rerun 385 TFLs around DBL |

Risk note 385 Rerun TFLs assigned against only 16 Leo hours — confirm whether additional team members carry the bulk of execution DBL-driven rerun; ensure snapshot schedule is confirmed with Abbvie

## REQ6710 — G_040_ONC_M23_001

| Sponsor | Abbvie |
| --- | --- |
| Study | G_040_ONC_M23_001 |
| Request | REQ6710 |
| Leo H. hours | 20 hrs |
| Rerun ADaM | 54 |
| New TFL | 10 |
| Rerun TFL | 0 |
| SOW | Rerun 54 tables + 10 new TFLs |

# 3. Projects Supported by Leo Hong

Beyond his own requests, Leo provides cross-project support hours to 4 studies. These commitments account for 84 hrs — the majority of his project time.

## REQ6076 — G_040_HEMONC_E01_DLBCL_ISS  (40 hrs)

| Owner | Lillian Dai |
| --- | --- |
| Leo H. hours | 40 hrs — highest single allocation this month |
| Rerun ADaM | 15 |
| Rerun TFL | 289 |
| SOW | Address ADaM/TFL cross-functional comments, draft ADRG, define outputs |

Attention 40 hours is Leo's largest single commitment — nearly 4 full working days on a support role Scope includes ADRG drafting which is high-complexity; confirm deliverable timeline with Lillian Dai

## REQ6621 — G_040_ONC_M19_708  (20 hrs)

| Owner | Mouctar Barry |
| --- | --- |
| Leo H. hours | 20 hrs |
| Rerun TFL | 158 |
| Deadline | Final delivery: 10 Apr 2026 |
| SOW | Update TFLs as per sponsor comment, final delivery |

Deadline alert Hard deadline: 10 April 2026 — earliest delivery in Leo's April schedule Confirm QC completion plan with Mouctar Barry

## REQ6685 — G_040_ONC_M19_611  (16 hrs)

| Owner | David Xu |
| --- | --- |
| Leo H. hours | 16 hrs |
| New TFL | 20 |
| Rerun TFL | 60 |
| DBL | 6 / 12 / 2026 |
| SOW | aCSR — TOC ready beginning of April; long-horizon project |

## REQ6637 — G_040_HEMONC_M21_103  (8 hrs)

| Owner | Summer Yang |
| --- | --- |
| Leo H. hours | 8 hrs |
| Rerun ADaM | 10 |
| Rerun TFL | 32 |
| Draft TFL | 4 / 7 / 2026 |
| Final TFL | 4 / 17 / 2026 |

# 4. Risk Summary & Recommended Actions

| Risk | Description | Priority | Action |
| --- | --- | --- | --- |
| Zero buffer | All 144 project hrs fully allocated; PTO reduces effective capacity further | High | Flag to manager before accepting any new ad-hoc requests in April |
| REQ6076 scope | 40 hrs on a support role with ADRG drafting — complex deliverable | High | Confirm scope boundary and deliverable timeline with Lillian Dai |
| REQ6621 deadline | Hard final delivery 10 Apr — earliest deadline in April schedule | High | Prioritise QC handoff with Mouctar Barry in week 1 |
| REQ6069 hours vs volume | 385 Rerun TFLs vs 16 Leo hrs — allocation gap | Medium | Confirm team execution plan; Leo likely reviewing only |
| Unplanned buffer | 24 hrs reserved — if consumed, other tasks compress | Medium | Monitor; escalate if unplanned work exceeds 24 hrs |

Generated: 2026-03-31